## Sheet1
Module | Step | Sub-step
Preparedness | Prepare and analyse | Secondary data review and analysis
Preparedness | Prepare and analyse | Primary data collection and analysis
Preparedness | Prepare and analyse | Baseline documentation
Preparedness | Prepare and analyse | Scenario development
Preparedness | Prepare and analyse | Build stakeholder engagement in CTP Preparedness
Preparedness | Prepare and analyse | Preparedness gap analysis and self-assessment
Preparedness | Prepare and analyse | Develop and implement key advocacy messages
Preparedness | Develop and implement | Appointment a NS CTP focal point
Preparedness | Develop and implement | Establish a CTP technical working group
Preparedness | Develop and implement | Develop CTP preparedness plan of action
Preparedness | Develop and implement | Develop CTP SOPs
Preparedness | Develop and implement | Mainstream CTP into strategic, contigency and response plans
Preparedness | Develop and implement | Incorporate CTP into HR systems
Preparedness | Develop and implement | Incorporate CTP into financial systems
Preparedness | Develop and implement | Incorporate CTP into M&E systems
Preparedness | Develop and implement | Incorporate CTP into RM systems
Preparedness | Develop and implement | Conduct a simulation and/or pilot
Preparedness | Develop and implement | Internal and external coordination of CTP actions
Preparedness | Develop and implement | Develop and implement CTP comms and awareness materials
Preparedness | Review, learn and improve | Creating a learning environment
Preparedness | Review, learn and improve | Internal review of CTP operations
Preparedness | Review, learn and improve | External evaluation of CTP operations
Preparedness | Review, learn and improve | Document and disseminate learning
Assessment | Planning and preparation | Explore response options
Assessment | Planning and preparation | Check if cash is feasible
Assessment | Planning and preparation | Compare modalities and mechanisms
Assessment | Planning and preparation | Conduct thorough risk analysis
Assessment | Planning and preparation | Calculate cost-efficiency
Assessment | Planning and preparation | Compare options and make a decision
Assessment | Cash sensitive community assessment | Get cash-specific information from the community
Assessment | Cash sensitive community assessment | Understand access to markets and financial services
Assessment | Cash sensitive community assessment | Identify and quantify priority needs
Assessment | Cash sensitive community assessment | Consolidate community findings
Assessment | Rapid market assessment | Identify key commodities & markets
Assessment | Rapid market assessment | Collect market information
Assessment | Rapid market assessment | Consolidate market findings
Assessment | Service providers, organisational capacity and risk analysis | Assess financial services
Assessment | Service providers, organisational capacity and risk analysis | Assess organisational capacity
Assessment | Service providers, organisational capacity and risk analysis | Analyse risks
Response Analysis | Feasibility, modality and mechanism selection | Explore response options
Response Analysis | Feasibility, modality and mechanism selection | Check if cash is feasible
Response Analysis | Feasibility, modality and mechanism selection | Compare modalities and mechanisms
Response Analysis | Feasibility, modality and mechanism selection | Conduct thorough risk analysis
Response Analysis | Feasibility, modality and mechanism selection | Calculate cost-efficiency
Response Analysis | Feasibility, modality and mechanism selection | Compare options and make a decision
Response Analysis | Decisions on the transfer value | Set the value
Response Analysis | Decisions on the transfer value | Adjust the value
Response Analysis | Targeting decisions | Identify most affected areas
Response Analysis | Targeting decisions | Identify targeting criteria & mechanisms
Set-up & Implementation | Programme set-up | Develop CTP operational plan
Set-up & Implementation | Programme set-up | Internal coordination
Set-up & Implementation | Programme set-up | Coordination with other actors
Set-up & Implementation | Beneficiary communication & accountability | Develop a BCA plan
Set-up & Implementation | Beneficiary communication & accountability | Build staff capacity
Set-up & Implementation | Beneficiary communication & accountability | Select communication channels & tools
Set-up & Implementation | Beneficiary communication & accountability | Develop messages for target audience
Set-up & Implementation | Beneficiary communication & accountability | Develop feedback and complaint mechanism
Set-up & Implementation | Beneficiary communication & accountability | Review & learn
Set-up & Implementation | Service provider contracting | Research potential service providers
Set-up & Implementation | Service provider contracting | Tendering process & service provider selection
Set-up & Implementation | Service provider contracting | Contract & define ways of work
Set-up & Implementation | Service provider contracting | Beneficiary data management & protection
Set-up & Implementation | Registration & identification | Plan & prepare for registration
Set-up & Implementation | Registration & identification | Identification & authentication
Set-up & Implementation | Distribution & encashment | Training & communication
Set-up & Implementation | Distribution & encashment | Planning & implementing distributions
Set-up & Implementation | Distribution & encashment | Encashment planning
Set-up & Implementation | Distribution & encashment | Encashment implementation
Monitoring & Evaluation | CTP M&E planning | Develop M&E strategy
Monitoring & Evaluation | CTP M&E planning | Build staff capacity
Monitoring & Evaluation | Programme monitoring | Baseline
Monitoring & Evaluation | Programme monitoring | Encashment monitoring
Monitoring & Evaluation | Programme monitoring | Post-distribution monitoring
Monitoring & Evaluation | Market monitoring | Monitor traders
Monitoring & Evaluation | Market monitoring | Monitor price data
Monitoring & Evaluation | Market monitoring | Respond to price changes
Monitoring & Evaluation | CTP evaluation | Set evaluation criteria & questions
Monitoring & Evaluation | CTP evaluation | Prepare evaluation ToRs
Monitoring & Evaluation | CTP evaluation | Generate reports